BASELINE SCHEDULE

Project Duration: 71 Working Days

Start Date: September 22, 2025

End Date: December 1, 2025

Project Manager:

# BASELINE SCHEDULE

| Project Tasks with Timeline |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| WBS Code | Task/Activity | Duration (Days) | Start Date | End Date | Resources |
| 1.0 | Project Initiation | 5 | Sep 22, 2025 | Sep 26, 2025 | 2 |
| 1.1 | Define objectives & scope | 2 | Sep 22, 2025 | Sep 23, 2025 | 2 |
| 1.2 | Identify stakeholders | 1 | Sep 24, 2025 | Sep 24, 2025 | 1 |
| 1.3 | Project charter approval | 2 | Sep 25, 2025 | Sep 26, 2025 | 2 |
| 2.0 | Requirement Analysis | 7 | Sep 27, 2025 | Oct 3, 2025 | 3 |
| 2.1 | Gather functional requirements | 3 | Sep 27, 2025 | Sep 29, 20252 | 2 |
| 2.2 | Gather non-functional requirements | 2 | Sep 30, 2025 | Oct 1, 2025 | 2 |
| 2.3 | Draft & approve SRS | 2 | Oct 2, 2025 | Oct 3, 2025 | 3 |
| 3.0 | System Design | 8 | Oct 4, 2025 | Oct 11, 2025 | 3 |
| 3.1 | Database design | 3 | Oct 4, 2025 | Oct 6, 2025 | 2 |
| 3.2 | UI/UX design | 3 | Oct 7, 2025 | Oct 9, 2025 | 2 |
| 3.3 | System architecture | 2 | Oct 10, 2025 | Oct 11, 2025 | 3 |
| 4.0 | Development | 25 | Oct 12, 2025 | Nov 5, 2025 | 4 |
| 4.1 | Backend development | 14 | Oct 12, 2025 | Oct 25, 2025 | 2 |
| 4.2 | Frontend development | 11 | Oct 26, 2025 | Nov 5, 2025 | 2 |
| 5.0 | Testing | 10 | Nov 6, 2025 | Nov 15, 2025 | 3 |
| 5.1 | Unit testing | 3 | Nov 6, 2025 | Nov 8, 2025 | 2 |
| 5.2 | Integration testing | 3 | Nov 9, 2025 | Nov 11, 2025 | 2 |
| 5.3 | UAT (students, supervisors) | 4 | Nov 12, 2025 | Nov 15, 2025 | 3 |
| 6.0 | Deployment | 5 | Nov 16, 2025 | Nov 20, 2025 | 2 |
| 6.1 | Setup hosting & DB | 2 | Nov 16, 2025 | Nov 17, 2025 | 2 |
| 6.2 | Deploy system | 2 | Nov 18, 2025 | Nov 19, 2025 | 2 |
| 6.3 | Finalize & go-live | 1 | Nov 20, 2025 | Nov 20, 2025 | 2 |
| 7.0 | Documentation | 7 | Nov 21, 2025 | Nov 27, 2025 | 2 |
| 7.1 | User manuals | 3 | Nov 21, 2025 | Nov 23, 2025 | 1 |
| 7.2 | Technical documents | 2 | Nov 24, 2025 | Nov 25, 2025 | 2 |
| 7.3 | Final project report | 2 | Nov 26, 2025 | Nov 27, 2025 | 2 |
| 8.0 | Project Closure | 4 | Nov 28, 2025 | Dec 1, 2025 | 2 |
| 8.1 | Final evaluation & presentation | 2 | Nov 28, 2025 | Nov 29, 2025 | 4 |
| 8.2 | Submission & sign-off | 2 | Nov 30, 2025 | Dec 1, 2025 | 2 |

SLACK CALCULATIONS.

Formula: Slack = LS - ES = LF - EF

Where:

ES = Early Start (earliest time a task can begin)

EF = Early Finish (earliest time a task can end)

LS = Late Start (latest time a task can begin without delaying project)

LF = Late Finish (latest time a task can end without delaying project)

| WBS | Task/Activity | ES | EF | LS | LF | Total Slack | Free Slack |  | Critical Path |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | Project Initiation | 0 | 5 | 0 | 5 | 0 | 0 |  | ✓ YES |
| 2.0 | Requirement Analysis | 5 | 12 | 5 | 12 | 0 | 0 |  | ✓ YES |
| 3.0 | System Design | 12 | 20 | 12 | 20 | 0 | 0 |  | ✓ YES |
| 4.0 | Development | 20 | 45 | 20 | 45 | 0 | 0 |  | ✓ YES |
| 5.0 | Testing | 45 | 55 | 45 | 55 | 0 | 0 |  | ✓ YES |
| 6.0 | Deployment | 55 | 60 | 55 | 60 | 0 | 0 |  | ✓ YES |
| 7.0 | Documentation | 60 | 67 | 60 | 67 | 0 | 0 |  | ✓ YES |
| 8.0 | Project Closure | 67 | 71 | 67 | 71 | 0 | 0 |  | ✓ YES |

Critical Path Analysis

Critical Path: 1.0 → 2.0 → 3.0 → 4.0 → 5.0 → 6.0 → 7.0 → 8.0

Total Project Duration: 71 working days

Critical Path Length: 71 days (100% of project duration)

Key Findings:

- All tasks are on the critical path - Every phase has zero slack.

- No buffer time available - Any delay will directly impact project completion.

- High schedule risk - Project requires strict timeline adherence.

- Dependencies are sequential - Each phase depends on the previous one.

RISK AREAS:

- Development Phase (25 days) - Longest duration, highest risk of delays

- Testing Phase (10 days) - Critical for quality, cannot be compressed

- Requirement Analysis (7 days) - Errors here propagate through all phases

Recommendations:

- Daily Progress Monitoring - Track completion % daily for all critical tasks

- Resource Buffering - Keep backup resources available for critical phases

- Early Risk Mitigation - Address potential delays immediately

- Parallel Activities - Where possible, overlap non-dependent subtasks

- Fast-Track Development - Consider agile sprints to identify issues early

- Contingency Planning - Prepare alternative approaches for high-risk tasks

PROJECT CALENDAR

September 2025

Mo Tu We Th Fr Sa Su

22 23 24 25 26 27 28 ← Project Initiation

29 30

October 2025

Mo Tu We Th Fr Sa Su

01 02 03 04 05 06 07 ← Requirement Analysis → System Design

08 09 10 11 12 13 14 ← Development begins

15 16 17 18 19 20 21

22 23 24 25 26 27 28

29 30 31

November 2025

Mo Tu We Th Fr Sa Su

01 02 03 04 05 06 07 ← Development ends → Testing begins

08 09 10 11 12 13 14

15 16 17 18 19 20 21 ← Deployment

22 23 24 25 26 27 28 ← Documentation

29 30

December 2025

Mo Tu We Th Fr Sa Su

01 02 03 04 05 06 07 ← Final Presentation

WORKING DAYS

Total Days Breakdown:

- Total Calendar Days: 71 days (Sep 22 - Dec 1, 2025)

- Working Days: 50 days

- Weekends: 20 days

- Public Holidays: 1 day (Oct 9 - Independence Day)

- Total Non-Working Days: 21 days

Working Days:

| Phase | Working Days | % of Total |
| --- | --- | --- |
| Project Initiation | 5 | 7% |
| Requirement Analysis | 7 | 10% |
| System Design | 8 | 11% |
| Development | 25 | 35% |
| Testing | 10 | 14% |
| Deployment | 5 | 7% |
| Documentation | 7 | 10% |
| Project Closure | 4 | 6% |
| TOTAL | 71 | 100% |

# MILESTONES SCHEDULE

| Milestone | Date | Phase | Deliverable |
| --- | --- | --- | --- |
| Project Charter Approved | Sep 26 2025 | Initiation | Approved project charter document |
| Requirements Finalized | Oct 3 2025 | Analysis | Software Requirements Specification |
| Design Complete | Oct 11 2025 | Design | ERD, UI/UX wireframes, architecture |
| Development Complete | Nov 5 2025 | Development | Functional web application |
| Testing Complete | Nov 15 2025 | Testing | Test reports, bug fixes completed |
| System Go-Live | Nov 20 2025 | Deployment | Live system on production server |
| Documentation Complete | Nov 27 2025 | Documentation | User manuals , technical docs |
| Project Delivery | Dec 1 2025 | 2025 Closure Final report | Presentation, sign-off |

ASSUMPTIONS & CONSTRAINTS

Assumptions:

- All team members are available full-time throughout the project.

- Stakeholders provide timely feedback and approvals.

- Required technical resources (servers, software) are available.

- No major scope changes after requirement phase.

- Working week is Monday-Friday (5 days).

Constraints:

- Fixed deadline: December 1, 2025 (academic calendar requirement).

- Zero slack: No buffer time available for delays.

- Sequential dependencies: Phases must be completed in order.

- Resource limitations: Limited team size (7 members).

- Budget cap: USD 500,000 maximum.